## Cover Page
Clinical Safety Hazard Log - Digital Interoperability Platform
Programme | Operations and Assurance Services | Document Record ID Key
Sub-Prog / Project | Clinical Safety | Digital Interoperability Platform
Prog. Director | Martin Dennys | Status | Live
Owner | Ian Dugdale | Version | 1.6
Author | Ian Tomlinson | Version Date | 07.07.2020
Clinical Safety Hazard Log - Digital Interoperability Platform
Document Purpose
Copyright © 2020, Health and Social Care Information Centre. NHS Digital is the trading name of the Health and Social Care Information Centre.All Rights Reserved.
This hazard log records generic hazards, they are provided as a starting point only and are not to be considered definitive. They are presented in a consistent form providing a hazard name, description, potential clinical impact, possible cause(s). The hazard assessments, and controls within the hazard log must be reanalysed and the hazard log modified to include additional hazards and or causes specific to the system under assessment Hazard assessments, should be completed collaboratively by the Manufacturer and Health Organisation from the results of a hazard workshop such as that described in section 4 Clinical Risk analysis of DCB 0129 and DCB 0160 standards.

## Version History
Amendment History
Version | Date | Amendment History
0.1
Reviewers
This document must be reviewed by the following:
Name |  | Title / Responsibility | Date | Version
Approved
This document must be approved by the following:
Name |  | Title / Responsibility | Date | Version
Document Status:
The controlled copy of this document is maintained in the NHS Digital corporate network. Any copies of this document held outside of that area, in whatever format (e.g. paper, email attachment), are considered to have passed out of control and should be checked for currency and validity.

## NRL Hazard Log
Hazard Number | Hazard Name | Hazard Description | Potential Clinical Impact | Possible Causes | Existing Controls | Severity | Likelihood | Risk | Design | Test | Training | BPC | Severity | Likelihood | Risk | Summary of Actions/Notes | Owner | Status

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | No. of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term. | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
|  | Risk Acceptability | [5 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible severity | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required